## README
Inventory Replenishment & Supplier Performance Tracker
Sample project — demand vs. supply tracking, delivery discrepancy flagging & what-if scenarios
PURPOSE
Built to practise a workflow that comes up across procurement, inventory and materials planning
roles: tracking confirmed supplier order quantities and dates against a demand forecast, flagging
discrepancies (late or short deliveries), and running what-if scenarios on delays.
TABS
1. Demand Forecast — forecasted sales/replenishment demand by SKU and week.
2. Supplier Orders — order-level data: quantities, due dates, actual delivery dates. Status and
delay are calculated automatically, so discrepancies surface without
manually checking each line.
3. Stock Coverage Dashboard — rolls up demand vs. confirmed supply per SKU, flags items AT RISK.
4. What-If Scenario — pick a supplier and a delay (in days) to see the effect on stock
coverage before it happens — supports proactive reordering decisions.
HOW TO USE
Cells shaded YELLOW with BLUE text are the only inputs meant to be edited (order data on the
Supplier Orders tab, and the scenario inputs on the What-If tab). All other cells are formulas
and will recalculate automatically.
NOTE ON DATA
SKU, supplier and order data in this file is illustrative sample data built to demonstrate the
workflow and formulas — not real business data.
RELATED PROJECT
See the companion Supplier Sustainability Scorecard workbook, which scores these same four
suppliers on emissions, renewable energy use, certification and proximity alongside delivery
performance.

## Demand Forecast
Demand Forecast
Forecasted replenishment demand by SKU and week
SKU ID | Product | Week | Forecasted Demand (units)
SKU-A | Wireless Earbuds | 1 | 420
SKU-A | Wireless Earbuds | 2 | 420
SKU-A | Wireless Earbuds | 3 | 450
SKU-A | Wireless Earbuds | 4 | 450
SKU-A | Wireless Earbuds | 5 | 480
SKU-A | Wireless Earbuds | 6 | 480
SKU-B | Phone Case (Bulk Pack) | 1 | 800
SKU-B | Phone Case (Bulk Pack) | 2 | 800
SKU-B | Phone Case (Bulk Pack) | 3 | 820
SKU-B | Phone Case (Bulk Pack) | 4 | 850
SKU-B | Phone Case (Bulk Pack) | 5 | 850
SKU-B | Phone Case (Bulk Pack) | 6 | 900
SKU-C | USB-C Charging Cable | 1 | 300
SKU-C | USB-C Charging Cable | 2 | 300
SKU-C | USB-C Charging Cable | 3 | 300
SKU-C | USB-C Charging Cable | 4 | 320
SKU-C | USB-C Charging Cable | 5 | 320
SKU-C | USB-C Charging Cable | 6 | 340
SKU-D | Laptop Stand | 1 | 260
SKU-D | Laptop Stand | 2 | 260
SKU-D | Laptop Stand | 3 | 280
SKU-D | Laptop Stand | 4 | 280
SKU-D | Laptop Stand | 5 | 300
SKU-D | Laptop Stand | 6 | 300

## Supplier Orders
Supplier Orders
Order-level tracking — Status and Delay (days) are calculated automatically
Order ID | Supplier | SKU ID | Product | Order Qty | Confirmed Qty | Due Date | Actual Delivery Date | Delay (days) | Status
PO-1001 | Supplier Alpha | SKU-A | Wireless Earbuds | 420 | 420 | 2026-10-05 | 2026-10-04 | -1 | On Time
PO-1002 | Supplier Alpha | SKU-A | Wireless Earbuds | 420 | 420 | 2026-10-12 | 2026-10-12 | 0 | On Time
PO-1003 | Supplier Alpha | SKU-A | Wireless Earbuds | 450 | 400 | 2026-10-19 | 2026-10-19 | 0 | On Time but Short
PO-1004 | Supplier Alpha | SKU-A | Wireless Earbuds | 450 | 450 | 2026-10-26 | 2026-10-27 | 1 | Late
PO-1005 | Supplier Alpha | SKU-A | Wireless Earbuds | 480 | 480 | 2026-11-02 | 2026-11-01 | -1 | On Time
PO-1006 | Supplier Alpha | SKU-A | Wireless Earbuds | 480 | 480 | 2026-11-09 |  |  | Pending
PO-2001 | Supplier Beta | SKU-B | Phone Case (Bulk Pack) | 800 | 800 | 2026-10-05 | 2026-10-05 | 0 | On Time
PO-2002 | Supplier Beta | SKU-B | Phone Case (Bulk Pack) | 800 | 800 | 2026-10-12 | 2026-10-12 | 0 | On Time
PO-2003 | Supplier Beta | SKU-B | Phone Case (Bulk Pack) | 820 | 820 | 2026-10-19 | 2026-10-19 | 0 | On Time
PO-2004 | Supplier Beta | SKU-B | Phone Case (Bulk Pack) | 850 | 850 | 2026-10-26 | 2026-10-29 | 3 | Late
PO-2005 | Supplier Beta | SKU-B | Phone Case (Bulk Pack) | 850 | 850 | 2026-11-02 | 2026-11-02 | 0 | On Time
PO-2006 | Supplier Beta | SKU-B | Phone Case (Bulk Pack) | 900 | 900 | 2026-11-09 |  |  | Pending
PO-3001 | Supplier Gamma | SKU-C | USB-C Charging Cable | 300 | 300 | 2026-10-05 | 2026-10-05 | 0 | On Time
PO-3002 | Supplier Gamma | SKU-C | USB-C Charging Cable | 300 | 280 | 2026-10-12 | 2026-10-14 | 2 | Late & Short
PO-3003 | Supplier Gamma | SKU-C | USB-C Charging Cable | 300 | 300 | 2026-10-19 | 2026-10-19 | 0 | On Time
PO-3004 | Supplier Gamma | SKU-C | USB-C Charging Cable | 320 | 320 | 2026-10-26 | 2026-10-28 | 2 | Late
PO-3005 | Supplier Gamma | SKU-C | USB-C Charging Cable | 320 | 320 | 2026-11-02 | 2026-11-01 | -1 | On Time
PO-3006 | Supplier Gamma | SKU-C | USB-C Charging Cable | 340 | 340 | 2026-11-09 |  |  | Pending
PO-4001 | Supplier Delta | SKU-D | Laptop Stand | 260 | 260 | 2026-10-05 | 2026-10-05 | 0 | On Time
PO-4002 | Supplier Delta | SKU-D | Laptop Stand | 260 | 260 | 2026-10-12 | 2026-10-11 | -1 | On Time
PO-4003 | Supplier Delta | SKU-D | Laptop Stand | 280 | 280 | 2026-10-19 | 2026-10-23 | 4 | Late
PO-4004 | Supplier Delta | SKU-D | Laptop Stand | 280 | 280 | 2026-10-26 | 2026-10-26 | 0 | On Time
PO-4005 | Supplier Delta | SKU-D | Laptop Stand | 300 | 300 | 2026-11-02 | 2026-11-02 | 0 | On Time
PO-4006 | Supplier Delta | SKU-D | Laptop Stand | 300 | 300 | 2026-11-09 |  |  | Pending

## Stock Coverage Dashboard
Stock Coverage Dashboard
Forecasted demand vs. confirmed supply, by SKU (totals across all weeks / orders)
SKU ID | Product | Total Forecasted Demand | Total Confirmed Supply | Coverage % | Status
SKU-A | Wireless Earbuds | 2700 | 2650 | 98.15% | AT RISK
SKU-B | Phone Case (Bulk Pack) | 5020 | 5020 | 100% | OK
SKU-C | USB-C Charging Cable | 1880 | 1860 | 98.94% | AT RISK
SKU-D | Laptop Stand | 1680 | 1680 | 100% | OK

## What-If Scenario
What-If Scenario: Supplier Delay Impact
Select a supplier and a hypothetical delay to see the effect on material coverage
Supplier to simulate: | Supplier Beta
Simulated delay (days): | 10
SKU ID | Product | Total Forecasted Demand | Total Confirmed Supply | Qty From Selected Supplier | At-Risk Qty (if delayed) | Adjusted Supply | Adjusted Coverage % | Impact
SKU-A | Wireless Earbuds | 2700 | 2650 | 0 | 0 | 2650 | 98.15% | OK
SKU-B | Phone Case (Bulk Pack) | 5020 | 5020 | 5020 | 5020 | 0 | 0% | AT RISK
SKU-C | USB-C Charging Cable | 1880 | 1860 | 0 | 0 | 1860 | 98.94% | OK
SKU-D | Laptop Stand | 1680 | 1680 | 0 | 0 | 1680 | 100% | OK
Try changing B4 (supplier) and B5 (delay days) to see which items move to AT RISK.
Assumption: for simplicity, any simulated delay (B5 > 0) treats that supplier's full confirmed quantity for the item as at-risk. A production MRP tool would isolate only the specific late order line(s) rather than the supplier's entire confirmed volume.